## Cover
Design Test Report
Version: 1.0
General Information
Project Name | Shein E-commerce website (https://ph.shein.com/)
Owner | Kyle Clarenz R. Lim
Project Type | Testing/Verification
Project Start Date | 4/15/2024
Project End Date | 4/20/2024
Product Description
Conduct testing to verify the quality of this website and ensure the website is released without any defects that may cause negative impact to the costumers and the business.
Revision History
Revision Date |  | Version | Author |  | Summary
4/15/2024 |  | 1 | Kyle Clarenz R. Lim |  | Initial draft. Includes testing of main website functionality and browser compatibility (Google Chrome & Microsoft Edge only)
Reviewer Information
Name |  | Department |  | Position
Karen Marie Igcasan |  | Education and Training |  | Instructor
Lenard Cordial |  | Education and Training |  | Instructor
Approver Information
Name |  | Department |  | Position
Michael Choi |  | Executive |  | Chief Executive Officer

## TEST SUMMARY REPORT
Test Report
Test Cycle | System Test
EXECUTED | PASSED |  |  | 60
| FAILED |  |  | 4
| (Total) TESTS EXECUTED (PASSED + FAILED) |  |  |  | 64
PENDING |  |  |  |  | 0
IN PROGRESS |  |  |  |  | 0 |  |  | Defect fixed | Not fixed
BLOCKED |  |  |  |  | 0 |  |  | 22 | 0
(Sub-Total) TEST PLANNED |  |  |  |  | 64
(PENDING + IN PROGRESS + BLOCKED + TEST EXECUTED)
Module | Description | % TCs Executed | % TCs Passed | TCs pending | Priority | Number of Test Cases | Number of defects | Defect fixed
Sign In & Register | Verify if user login authentication and registration function is working | 100% | 100% | 0 | High | 8 | 0 | 0
Sign In & Register | Verify if user login authentication and registration function is working | 100% | 100% | 0 | Medium | 1 | 0 | 0
Home | Verify if user interaction based functions in the Home page is working. | 100% | 100% | 0 | High | 9 | 0 | 0
Home | Verify if user interaction based functions in the Home page is working. | 100% | 66.66% | 0 | Medium | 3 | 1 | 0
Item Detail | Verify if user interaction based functions in the Items page is working. | 100% | 100% | 0 | High | 5 | 0 | 0
Item Detail | Verify if user interaction based functions in the Items page is working. | 100% | 100% | 0 | Low | 2 | 0 | 0
Cart | Verify if user interaction based functions in the Cart page is working. | 100% | 100% | 0 | High | 4 | 0 | 0
Cart | Verify if user interaction based functions in the Cart page is working. | 100% | 100% | 0 | Medium | 3 | 0 | 0
User Detail | Verify if user interaction based functions in the User Detail page is working. | 100% | 100% | 0 | High | 11 | 0 | 0
User Detail | Verify if user interaction based functions in the User Detail page is working. | 100% | 100% | 0 | Medium | 5 | 0 | 0
Wishlist | Verify if user interaction based functions in the Wishlist page is working. | 100% | 100% | 0 | High | 1 | 0 | 0
Wishlist | Verify if user interaction based functions in the Wishlist page is working. | 100% | 100% | 0 | Medium | 4 | 0 | 0
Checkout & Payment | Verify if user interaction based functions in the Checkout page is working. | 100% | 100% | 0 | High | 5 | 0 | 0
Browser Compatibility Defects | Comparing user experience on Google Chrome and Microsoft Edge browser. | 100% | 100% | 0 | Low | 3 | 3 | 3
Defect ID | Bug description |  |  | Test Case ID | Priority | Severity | Open date | Status | Raised By | Tested on Version
| Steps to Reproduce | Expected Results | Actual Results
1 | 1) Enter search item keyword to the search bar (special characters): !@#^&* 2) Click Search button | Should be able to throw "No results found" message | Is redirected to page with random women apparel items displayed | HM10 | Medium | Low | 2024-04-16 | Open | Kyle Lim | v1
2 | Click Cart button | Should be redirected to Cart page and show percent discount notice in the upper left side of item image with the same background color for each browser | Is redirected to Cart page and show percent discount notice in the upper left side of item image but with not the same background color for each browser (orange for Chrome; black for edge) | BCM01 | Low | Low | 2024-04-16 | Open | Kyle Lim | v1
3 | Click Cart button | Should be redirected to Cart page and show free shipping notice in the upper right side of the Checkout Now button for each browser | Is redirected to Cart page but not showing the free shipping notice in the upper right side of the Checkout Now button for the Microsoft Edge browser | BCM02 | Low | Low | 2024-04-16 | Open | Kyle Lim | v1
4 | Click Cart button | Should be redirected to Cart page and shows pop up notice for positive reviews that pop in and out every 5 seconds for each browser | Is redirected to Cart page and does not shows pop up notice for positive reviews in the Chrome browser | BCM03 | Low | Low | 2024-04-16 | Open | Kyle Lim | v1

## Sheet1
Defects by Priority |  |  | Defect by Severity |  |  | Defects by Module
| Priority | Test Case Count |  | Priority | Test Case Count |  | Module | Number of Defects
| Low | 3 |  | Low | 4 |  | Sign In & Register | 0
| Medium | 1 |  | Medium | 0 |  | Home | 1
| High | 0 |  | High | 0 |  | Item Detail | 0
[7 empty] | Cart | 0
[7 empty] | User Detail | 0
[7 empty] | Wishlist | 0
[7 empty] | Checkout & Payment | 0
[7 empty] | Browser Compatibility Defects | 3
Defects by Priority
| Stauts | Ratio
| Fixed | 0
| Not Fixed | 100